Lymphoedema Network Northern Ireland (LNNI)

Annual Report 2010/11

Agreement Cover Sheet

This annual report has been agreed by:

Chair of LNNI Board

Name: 		Mrs Clare McGartland

Date agreed            8th June 2011

LNNI Project Lead

Name: 		Ms Jane Rankin

Date agreed            8th June 2011

LNNI Project Manager

Name: 		Ms Debbie Schofield

Date agreed            8th June 2011

LNNI Board members agreed the report on

Date agreed            21st June 2011

Annual report review date: AGM, June 2012

- Introduction

This report relates to work undertaken by the Lymphoedema Network Northern Ireland (LNNI) during the year 2010/11.

- Clinical Lead’s address

The Lymphoedema Network Northern Ireland Board has continued to provide an executive platform regarding leadership and direction to the work of the network whilst ensuring that all those with lymphoedema in Northern Ireland have equal access to high quality person centred care. All regional networks are currently undergoing a modernisation review and LNNI has been advised to continue with their proposed work plan throughout this period.

Representation on the Board includes:

- 5 service users

- Clinical leads from each trust

- Commissioner

- General Practitioner

- Secondary Care Directorate, DHSSPS

- DHSSPSNI Deputy Director of Secondary Care (until September 2010)

- Assistant Director of commissioning for Regional Services and Strategic Planning, Health and Social Care Board (from September 2010)

- LNNI Project team (chair, lead and manager)

The project team would again like to acknowledge the continuous energy and support of the Board; all members have worked consistently and effectively to develop the profile of lymphoedema in Northern Ireland. LNNI has recently been invited to join the International Lymphoedema Framework (ILF) which recognises the achievement in standards of lymphoedema management and models of service provision. As we await the result of the regional network review, we hope that the outcomes will support the continuation of the Board and of the valuable work being achieved for patients with lymphoedema in Northern Ireland.

- Background and rationale

In 2002 the Chief Medical Officer commissioned a review of regional lymphoedema services. The Report of the Lymphoedema Services Review Group (2004) included several recommendations including:

- Development of a CREST lymphoedema guideline

- Development of a managed clinical network to coordinate  regional    lymphoedema service development

- Development of specialist lymphoedema therapists (with   appropriate     progressive training)

- Prevention and early detection strategies aimed at healthcare professionals, patients and the public

The Lymphoedema Network Northern Ireland (LNNI) was launched at a on 1st February 2008 and its vision is to change the emerging picture of the condition over the next 5 -10 years by initiating an early screening programme, awareness campaign and improved clinic access which will be supported by the cardiovascular and cancer service frameworks.

4.0	Meetings schedule and attendance 2010/11

For decision making / approval 60% of key members with a minimum of one patient representative, one trust clinical lead, one stakeholder, and one member from the management team must be present. All meetings achieved the required quorum.

|  | 8th June 2010 | 14th Sept 10 | Dec 10 – cancelled due to severe weather (snow) | 8th March 11 |
| --- | --- | --- | --- | --- |
| PPI | √ | √ |  | √ |
| Trust clinical lead | √ | √ |  | √ |
| Trust SMT representative | √ | √ |  | √ |
| Commissioner | √ | √ |  | √ |
| LNNI Mgt team | √ | √ |  | √ |
| More than 60% Board membership | √ | √ |  | √ |

5.0 Patient and Carer Feedback Involvement

Five patient representatives (or alternates), one per trust, regularly attended Board meetings and associated project meetings e.g. development of new patient information leaflets, and participated in electronic (e-mail) document reviews and additional communications. This has enriched discussion and ensured that patient voice is at the centre of the group’s work.

Written patient information is consistently identified as a priority by patients.  As such, one of the 2010 projects consisted of a project which developed 8 new adjunct information leaflets to support the teaching provided by the therapists. This was deemed to be a priority in respect of the life-long nature of the condition and the need for patients to become more independent and expert in the management of their own lymphoedema.

Regional patient stakeholder events have been held regularly since 2008 but the emerging views of the participants stated that whilst it was interesting to be involved at regional level, more people wanted to be active at trust level where they felt they could more effectively influence the care provided to patients in their area. The majority of this feeling came from the more rural areas; in response to this request, the trust leads from the Southern and Northern Trusts initiated their own smaller groups which have PPI leadership and support of the trust team. The South Eastern lead, just back from maternity leave, had this trust’s first meeting in May 2011. The Western Trust lead, also just back from maternity leave and relatively newly in post is also planning a meeting for the autumn. Meeting details are updated regularly on the LNNI website (www.lnni.org)

- Key Achievements

Throughout the 3rd year (Feb 2010 - 11) LNNI have:

- Continued to develop the website www.lnni.org : a resource for patients, the public and health care professionals

- Continued to lead the regional complex clinic, but have reduced the clinics to 3 per year in recognition of skill up-grading and service need

- Started population of the regional minimum dataset for lymphoedema (Lymphdat), developed initial report formats and drafted first demographic/aetiology review (to be signed off by Board at 2011 AGM)

- Reviewed the network governance arrangements (TOR, constitution and strategies) and clinical paperwork referral/assessment tools/policies (in line with Lymphdat format)

- Developed 8 new patient information adjunct leaflets to support self-management

- Won a BMA commendation for the non-cancer information booklet published in March 2010

- Engaged with stakeholders to plan and support local PPI intra-trust groups to influence services (Northern, Southern and South Eastern)

- Published reports for both the cancer and cardiovascular frameworks, including baseline figures and agreed annual performance measures for 2012 and 2013

- Audit (July 10) of services (cancer only) using the National Cancer Action Team rehabilitation symptom pathway project  - lymphoedema model and work plan developed

- Re-audit of CREST model (January 2011) and ongoing work plan with trust service managers

- Raised the profile of lymphoedema via various regional, national and international conference presentations, including masters level teaching

- Continued to lobby the Department of Health and Ministers regarding key issues affecting the service e.g. increasing levels of obesity

- Identified the growing impact of obesity on the services and published a paper which has been shared with the British Lymphology Society (BLS) and the ILF, and supports access to activity schemes and nutritional advice

- Developed new information regarding local access to activity schemes and weight management (on menu of www.lnni.org). All trusts encouraging participation in such schemes from time of assessment

- Research officer recruited (sponsored by Friends of Cancer Centre), protocol developed and ethics initiated for Bioimpedence screening project

- Research ongoing in partnership with the Macmillan Support and Information Centre regarding the psychological impact of lymphoedema and assessment of screening tools for clinical use

7.0	Key Challenges for 20011/12

7.1 NHS financial constraints

2010/11 has been a difficult year for all NHS services as a result of the severe financial constraints. This has meant that maternity leaves and other vacancies have not been recruited into; this will continue to impact on the services. The temporary loss of several band 3 posts in particular have affected skill mix with more senior staff covering clerical officer and assistant duties, thus reducing the service clinical capacity; this will continue to impact in 2011/12 unless there is an improvement in recruitment potential.

7.2 NHS Access/ waiting times target

The regional driver for all out-patient services i.e. the regional access (waiting time) target of 9 weeks (the time from receipt of referral to treatment) whilst having been met for the first half of 2010/11 has seen several recurring breaching patterns due to the staffing issues. The public relations and education activities of the network have continued to successfully raise referrals rates (869 in 2010) which have also impacted on access.

Education assessment and triage clinics have been beneficial to date at reducing DNS/CNAs figures (did not attend/ could not attend) and thereby improve access. Concurrently, as the teams from the trusts continue to modernise under their new leadership, this 9 week access target is being actively addressed, but will continue to be a challenge.

7.3 Prevalence rates

Prevalence rates continue to be a threat to service access, and goods and services budgets. Lymphoedema, as a long term condition, will always have an increasing prevalence rate as patients cannot, on the whole, be discharged due to the nature of the condition; patients will require monitoring and compression garments on an ongoing basis, thus necessitating the requirement of surveillance of this hidden challenge for both trust budgets and clinical cover.

The trust teams have implemented the practice of utilising joint acute and primary care prescribing, sharing the cost of goods; they have also discharged very stable patients to the care of their GP, and utilised band 3 support to monitor the less complex cases, at times using a formalised telephone review package. In 2010 there were 2204 review appointments.

7.4 Obesity rates

Obesity is becoming a great challenge to the services; more patients with a Body Mass Index (BMI) of over 40 i.e. who are recognised by NICE as being obese (level 3), are being referred more regularly into the service. Severe obesity affects the working of the lymphatics and will worsen existing levels. Whilst management will temporarily improve the situation, research has shown that those who are overweight are more likely to rapidly lose the benefit of treatment. Many of these patients also have mobility issues compounding the problem, as confirmed by the 2010 audit of the patients attending the complex clinic. Currently, this patient group utilise a large percentage of clinical time and raise the potential risk for manual handling trauma to either patient or therapist.

In response to this problem, the project team developed a GP postcard with essential diagnostic and referral information which was issued to all GPs and RCN members (in GP practices and nursing/residential homes) ; this aimed to encourage the concurrent, or prior, referral to obesity clinics (dietitian/ clinical psychologist services) and rehabilitation services along with the referral to the lymphoedema teams.

Several new initiatives will hopefully work towards addressing some issues: the new LNNI obesity pathway guidance, increased facilitation into trust and council led activity schemes/ weight management guidance and the move towards more self-led care. The new pathway has been shared with the Department of Health, the ILF and the BLS; MLAs have also been lobbied to enquire about access to obesity services which are currently unavailable regionally.

LNNI have also purchased 3 new bariatric treatment plinths to reduce the associated manual handling risk. A domiciliary risk assessment has also been shared with all the teams to highlight the need for additional handling aids to prevent trauma to both the patient and the therapist. However, this challenge is unlikely to resolve in the near future due to the lack of obesity management.

7.5 Education developments

A key aim of the network is to improve diagnostic skills and the facilitation of early referral, thereby influencing the chronic disease pattern and ultimately the prevalence. Whilst the University of Ulster undergraduate programme has been embedded into nursing, physiotherapy, occupational therapy, podiatry and radiotherapy, the challenges are to form partnerships with Queen’s University Belfast and also with the private sector; this is recognised as a long term investment.

7.6 Frameworks (cancer and cardio vascular)

The Network has submitted baseline reports for the cardio vascular and cancer frameworks.  The standards address access to “offered” care, patient information (both awareness information prior to developing lymphoedema and adjunct information provided whilst having lymphoedema management). Whilst results have been positive, new objectives have been set for 2012 and 2013. Recruitment issues may affect access, but information provision at time of treatment should progress rapidly in all teams. The offer of “at risk” information is dependent upon surgical and other teams, but this has been developed and printed by LNNI, and circulated to all potential referrers for distribution to at risk groups.

The cancer standard also addresses the issues of lymphoedema risk inclusion in the consent process and the use of screening techniques by surgical teams to ensure diagnosis and referral. The trust teams are lobbying for the former and hope that the LNNI research Bioimpedence screening project will inform and escalate the latter. However, it is anticipated that the latter may be a slow development as a result of the wide spread financial problems.

8.0	Work Plan 2010/11

Appendix A

For further information on the LNNI Board, please follow this link:  www.lnni.org

Appendix A

LNNI Work Plan

June 11 - March 12

Agreement Cover Sheet

This work programme has been agreed by:

Chair of LNNI     Clare McGartland

Date agreed        21st June 2011

LNNI members agreed the report on   21st June 2011

Annual report review date   AGM, June 2012

| Programme headings | Key projects/tasks | Progress |  | Current status | Jun-11 | July -11 | Aug -11 | Sept -11 | Oct -11 | Nov -11 | Dec -11 | Jan -12 | Feb -12 | Mar -12 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. Governance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | i. Terms of reference & constitution for board and local trust networks | All reviewed May 2010 |  |  | Review TOR etc |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | ii. Standards, targets and new policies | Reports for cancer and cardio vascular frameworks submitted May 11and Nov 10 respectively. Review both March 12 Obesity Policy (drafted winter/spring 2010/11). Shared with Dept, ILF and BLS April 2011 for feedback. |  |  | Board meeting: Report access target , sign off Obesity policy | Introduce Obesity Policy to practice |  | Report on access target at board meeting | Lobby re impact of obesity |  | Report on access target at board meeting |  |  | Report on access target at board meeting. Review both frameworks’ KPI data |  |  |  |  |  |  |  |  |
|  | iii. Monitor resources including finance | To be reported at each Board meeting in trust reports - leads |  |  | Board report |  |  | Board report |  |  | Board report |  |  | Board report |  |  |  |  |  |  |  |  |
|  | iv. Incident & complaints monitoring | To be reported at each Board meetings - protocol / line of comms agreed for information to be released from each trust to network - leads. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | v. Board meetings | Minutes & agendas ratified by board at following meeting & added to website – JR/DS |  |  | Sign off and up load |  |  | Sign off and upload |  |  | Sign off and up load |  |  | Sign off and up load |  |  |  |  |  |  |  |  |
| 2. Service development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | i. Report on existing services mapping | Mapping report complete – ratified by Board Dec 09 (Southern, South Eastern, Northern & Belfast HSC Trusts). Western Trust to start Sept11(when established after maternity leave) Private sector joint working commenced autumn 10 (Belfast) |  |  |  |  |  | WT mapping to start Begin linking with Northern private clinic |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | ii. Patient database Lymphdat | Population to began May 10. Funding from LNNI account agreed by Board (Mar 10-Jan 11) to pay for 0.5 wte band 3 to input records across all trust areas. Demographic/aetiology report – for June 11 AGM. Continue to develop reports and letters facilities |  |  | For sign off of report at AGM |  |  |  |  |  |  |  |  | Demographic/aetiology report 2012 |  |  |  |  |  |  |  |  |
|  | iii. Complex clinics | Clinic protocol, booking system & plan agreed with clinical team. Version 5.0 of policy ratified. Report complete Jan 10. Freq reduced to 3 per year in response to learning and patient need. |  |  | Clinic 17th June |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | iv. Clinical practitioner register | Service mapping tool will inform. Monitor and publish in each 6 month report - JR |  |  |  |  |  |  | 9th 6 month report |  |  |  |  | 10th 6 month report |  |  |  |  |  |  |  |  |
|  | v. Education strategy | Framework for strategy ratified by board (AGM June 09) and by public consultation via website. Update for AGM June 11: - Undergrad - specialist - awareness |  |  | UU nursing students | CS update | Working with QUB under grad | Working with private sector | Study days – NT & WT Awareness trg |  |  | Taping course TBC | Dermatology course |  |  |  |  |  |  |  |  |  |
| 3. Communication |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | i. Website maintenance | Update news, events & circulate newsletter |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | ii. Patient information leaflet | Cancer(08) and non-cancer (10): Links made with appropriate services re issuing New adjuncts published Mar 11 for use with teams. Will require a familiarisation period |  |  | Team familiarisation re new adjunct leaflets |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | iii. Newsletter | 5th edition of newsletter due July/August 11 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | iv. Stakeholders and external relationships | 250 Stakeholders registered. Leads to continue to encourage registration. Offered membership of the International Lymphatic Framework (May 11) |  |  | Membership agreed by e-mail but to be confirmed at board meeting |  | Integrate communications with ILF newsletter, website etc |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | v. Stakeholder events | Continued ST, NT and SET events. WT is start autumn 11. |  |  | SET PPI event |  | ST PPI event |  | NT PPI event | NILSG AGM | WT PPI event |  | ? multi-prof event |  |  |  |  |  |  |  |  |  |
|  | vi. Six month board report | Latest report produced 30th April 10, 31st Oct. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | vii. Communication strategy | Framework for strategy ratified by board (AGM 09)and public consultation via website. - Stephen Nolan Show & MLAs re obesity issues, Mar 11 - framework submissions - obesity policy submitted to Dept, ILF and BLS March 11 -GP Postcards, Aug10 & Feb 11 -Liaison with private health care institutions JR/GMcC, on going - private sector liaison - QUB liaison |  |  | Continue to develop QUB liaison re under grad Mike Philpot | Initiate discussion with Northern private clinic | Cont re obesity issue with BLS/ ILF |  | BLS conference - JR to attend to lobby |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | viii. Annual report | Due June 11 AGM (JR) |  |  | Sign off |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | i. Audit programme to monitor practice against agreed standards & targets | 1. Audit based on CREST standards & targets. 2. Cancer Action Team (national) CAT EBP Pathway audit |  |  |  | Re-audit CATs and action plan |  |  |  |  |  | Re- audit CREST and action plan |  |  |  |  |  |  |  |  |  |  |
|  | ii. User satisfaction & focus groups | As per 3v |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | New intra trust PPI groups | New intra trust PPI groups |
|  | iii. Monitor action plans | Action plan developed from Stakeholder Event Feb 10 Report - ratified by Board March 10. Continuous updates with service managers |  |  |  |  | Plan for intra trust PPI in WT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5. Research |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Research i. Clinical practice | Screening of breast cancer pts using bioimpedence |  |  | Board report | ethics | ethics | Board report | Begin recruitment |  | Board report |  |  |  |  |  |  |  |  |  |  |  |
|  | ii. Epidemiology | Initial demographic and aetiology report using Lymphdat data to highlight local trends. |  |  | Lymphdat report to be signed off at AGM | Propose as abstract for BLS conference |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | iii. Quality of life study | Work ongoing with Rachel Holland and psychology post grad. Bursary agreed by Board (Dec 09). Continued delay due to staffing issues in clinical psychology. Will inform QoL tool. |  |  | Meet with new project lead |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | iv. Exercise & lymphoedema | Grant proposal submitted to AHP cancer hub – Nov 11. For PhD interviews June 11 |  |  | Await PhD interview results |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Not yet started |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Behind schedule |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| On schedule |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Ahead of schedule |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Completed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | This project plan is signed on behalf of the LNNI Board by: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Chair: |  | Signature: |  |  |  | Date: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Ms Clare McGartland |  | _______________________ |  |  |  | 8th June 2011 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |